## Sheet1
TOGEL Platform Development Process | [5 empty] | 27/11/2017 --- 22/12/2017 | [21 empty] | 11/01/2018 --- 26/01/2018
Row | Task Title | Starting date | Ending Date | status | Description | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
1 | Designing the architecture of platform
2 | Starting the zero plat form to setup |  |  | done
3 | Authentication layer |  |  |  | Admin, Purchaser, Supplier dashboard panel
| Authentication layer - Registration |  |  | done
| Authentication layer - Token creation |  |  | done
| Authentication layer - Login form |  |  | done
| Authentication layer - Password Recovery |  |  | done
| Authentication layer - Controller |  |  | done
4 | Purchaser Dashboard
| Purchaser Dashboard - setup company profile |  |  | done | Controller, Views, Model, connecting to users
Purchaser Dashboard - homepage
| Purchaser Dashboard - Create Channel |  |  | done | Channel is quale to Sector in SIGIT defination Controller, Views and Model Create/edit/delete/list/auth
| Purchaser Dashboard - Create RFQ |  |  | done | Controller, Views and Model Create/edit/delete/list/auth/view all/ Adding the SIGIT variables (Type,Material, Dimension) Customizing the RFQ Specifications
| Purchaser Dashboard - RFQ - View Offers/compare offers |  |  | done | bar: 27/11/2017 --- 22/12/2017 6 to 27/11/2017 --- 22/12/2017 11
| Purchaser Dashboard - RFQ - View Offer - Accept/Reject an RFQ |  |  | done | bar: 27/11/2017 --- 22/12/2017 6 to 27/11/2017 --- 22/12/2017 11
| Purchaser Dashboard - RFQ - View Offer - Message to Supplier |  |  | done | bar: 27/11/2017 --- 22/12/2017 6 to 27/11/2017 --- 22/12/2017 11
| Purchaser Dashboard - RFQ - View Offer - Make a Deal |  |  | - | bar: 27/11/2017 --- 22/12/2017 6 to 27/11/2017 --- 22/12/2017 11
Purchaser Dashboard - RFQ - Cancel | bar: 27/11/2017 --- 22/12/2017 6 to 27/11/2017 --- 22/12/2017 11
| Purchaser Dashboard - RFQ - Invite a Supplier |  |  | done | bar: 27/11/2017 --- 22/12/2017 6 to 27/11/2017 --- 22/12/2017 11
| Purchaser Dashboard - RFQ - Search |  |  | done
| Purchaser Dashboard - Circle |  |  | done
| Purchaser Dashboard - Circle - Invite a company |  |  | done | bar: 11/01/2018 --- 26/01/2018 23 to 11/01/2018 --- 26/01/2018 26
| Purchaser Dashboard - Circle - Accept an invitation |  |  | done | bar: 11/01/2018 --- 26/01/2018 23 to 11/01/2018 --- 26/01/2018 26
Purchaser Dashboard - Circle - Cancel the relation | bar: 11/01/2018 --- 26/01/2018 23 to 11/01/2018 --- 26/01/2018 26
| Purchaser Dashboard - Circle - Send a Message |  |  | done | bar: 11/01/2018 --- 26/01/2018 23 to 11/01/2018 --- 26/01/2018 26
| Purchaser Dashboard - Create Template for RFQ |  |  | done | Controller, Views and Model Create/edit/delete/list/view Make a possibility to duplicat the request | bar: 27/11/2017 --- 22/12/2017 15 to 27/11/2017 --- 22/12/2017 18
| Purchaser Dashboard - Create RFQ by Import from template |  |  | done | Import to page and show to user | bar: 27/11/2017 --- 22/12/2017 15 to 27/11/2017 --- 22/12/2017 18
Purchaser Dashboard - catalogs | bar: 27/11/2017 --- 22/12/2017 19 to 27/11/2017 --- 22/12/2017 22
| Purchaser Dashboard - catalogs - Products |  |  |  | Controller, Views and Model Create/edit/delete/list/view | bar: 27/11/2017 --- 22/12/2017 19 to 27/11/2017 --- 22/12/2017 22
| Purchaser Dashboard - catalogs - Services |  |  |  | Controller, Views and Model Create/edit/delete/list/view | bar: 27/11/2017 --- 22/12/2017 19 to 27/11/2017 --- 22/12/2017 22
| Purchaser Dashboard - catalogs - Machines |  |  |  | Controller, Views and Model Create/edit/delete/list/view | bar: 27/11/2017 --- 22/12/2017 19 to 27/11/2017 --- 22/12/2017 22
5 | Supplier Dashboard | bar: 27/11/2017 --- 22/12/2017 1 to 27/11/2017 --- 22/12/2017 6
Supplier Dashboard - setup company profile | bar: 27/11/2017 --- 22/12/2017 1 to 27/11/2017 --- 22/12/2017 6
Supplier Dashboard - homepage | bar: 27/11/2017 --- 22/12/2017 1 to 27/11/2017 --- 22/12/2017 6
| Supplier Dashboard - Open a Channel |  |  | done | Search / Open | bar: 27/11/2017 --- 22/12/2017 1 to 27/11/2017 --- 22/12/2017 6
| Supplier Dashboard - Open an RFQ |  |  | done | bar: 27/11/2017 --- 22/12/2017 1 to 27/11/2017 --- 22/12/2017 6
| Supplier Dashboard - RFQ - Send an offer |  |  | done | bar: 27/11/2017 --- 22/12/2017 1 to 27/11/2017 --- 22/12/2017 6
| Supplier Dashboard - RFQ - View Offer |  |  | done | bar: 27/11/2017 --- 22/12/2017 1 to 27/11/2017 --- 22/12/2017 6
| Supplier Dashboard - RFQ - EDIT/CANECL Offer |  |  | done | bar: 27/11/2017 --- 22/12/2017 1 to 27/11/2017 --- 22/12/2017 6
| Supplier Dashboard - RFQ - View Offer - Message to Purchaser |  |  | done
Supplier Dashboard - My Offers | bar: 27/11/2017 --- 22/12/2017 12 to 27/11/2017 --- 22/12/2017 14
| Supplier Dashboard - My Offer - Cancel |  |  | done | bar: 27/11/2017 --- 22/12/2017 12 to 27/11/2017 --- 22/12/2017 14
| Supplier Dashboard - My Offer - View Status |  |  | done | bar: 27/11/2017 --- 22/12/2017 12 to 27/11/2017 --- 22/12/2017 14
| Supplier Dashboard - My Offer - Search an Offer |  |  | done | bar: 27/11/2017 --- 22/12/2017 12 to 27/11/2017 --- 22/12/2017 14
| Supplier Dashboard - Circle |  |  | done
| Supplier Dashboard - Circle - Invite a company |  |  | done | bar: 11/01/2018 --- 26/01/2018 23 to 11/01/2018 --- 26/01/2018 26
| Supplier Dashboard - Circle - Accept an invitation |  |  | done | bar: 11/01/2018 --- 26/01/2018 23 to 11/01/2018 --- 26/01/2018 26
| Supplier Dashboard - Circle - Cancel the relation |  |  | done | bar: 11/01/2018 --- 26/01/2018 23 to 11/01/2018 --- 26/01/2018 26
| Supplier Dashboard - Circle - Send a Message |  |  | done | bar: 11/01/2018 --- 26/01/2018 23 to 11/01/2018 --- 26/01/2018 26
6 | Database - Local Migration | bar: 11/01/2018 --- 26/01/2018 27 to 11/01/2018 --- 26/01/2018 29
Database - table's factory seeds | bar: 11/01/2018 --- 26/01/2018 27 to 11/01/2018 --- 26/01/2018 29
7 | Developing the Test Cases | bar: 11/01/2018 --- 26/01/2018 28 to 11/01/2018 --- 26/01/2018 32
8 | Integration with Industrial-Cloud | bar: 11/01/2018 --- 26/01/2018 30 to 11/01/2018 --- 26/01/2018 34
Integration - database migartions | bar: 11/01/2018 --- 26/01/2018 30 to 11/01/2018 --- 26/01/2018 34
Integration - users and actions | bar: 11/01/2018 --- 26/01/2018 30 to 11/01/2018 --- 26/01/2018 34